## Sheet1
| Board Chair | Board Members | Marketing Lead | Volunteer Lead | Project Manager
Complete venue contract | R / A | C | I | I | C | R | Responsible
Promote silent auction items on website | I | C | R / A | I | C | A | Accountable
Train event volunteers | I | I | I | R / A | C | C | Consult
Send invitations | I | I | C | R / A | C | I | Inform
Develop event agenda | I | C | I | I | R / A
Determine cost of event tickets | C | C | I | I | R / A
Promote event on social media | I | C | R / A | I | C
Research local venue | C | I | I | I | R / A
Procure silent auction items | R | R | I | I | A
Design invitations | I | I | R / A | I | C